## README
Demo 04 — Reverse stress test: what makes the budget break
Turn a static cost model into a Monte Carlo model, then work backwards from budget breaches to the inputs that cause them.
WHAT THIS DEMO SHOWS
A data-centre build has 8 work-breakdown lines and a hard 10,500 $k budget. Claude replaces each base cost with a PERT distribution, simulates, and then asks the reverse question: given that the budget was breached, which inputs did it?
The reverse stress test uses the recorded per-iteration joint samples, so it finds the combination of drivers behind breaches, not just one-at-a-time sensitivities.
Tools demonstrated: replace_constant_with_distribution, wrap_with_output, run_simulation, get_simulation_results, reverse_stress_test
GETTING STARTED
You need: Windows Excel with the ModelRisk add-in installed and licensed, and modelrisk-mcp connected to Claude (Claude Desktop or Claude Code).
Save the demo gallery folder anywhere on your PC. Once per session, tell Claude where it is and which demo to open:
PROMPT → My ModelRisk demo gallery is in <your folder, e.g. Documents\modelrisk-demos>. Open 04_reverse_stress_test.xlsx from there.
Claude remembers the folder for the rest of the session — later demos just need "Open <file> from the demo folder".
FAST TRACK — ONE PROMPT DOES IT ALL
In a hurry? This single prompt runs the whole demo end-to-end. Prefer to learn how it works? Skip to the numbered steps below — same result, one capability at a time.
PROMPT → In the Model sheet of this workbook, replace each base cost in B6:B13 with the matching distribution from column D, using the WBS line names as input names; wrap Total cost B15 as output "TotalCost"; run 5,000 iterations. Then report the chance the total exceeds the 10,500 budget and the P90 total, and run a reverse stress test: when TotalCost breaches 10,500, which inputs drive it and what does the typical breach scenario look like?
Expected: the forward risk view plus the breach-driver ranking and a named stress scenario.
STEP-BY-STEP
1 | Open the workbook and look at the Model sheet: 8 WBS lines with base costs (blue inputs) and suggested distributions in column D.
PROMPT → Open 04_reverse_stress_test.xlsx from the demo folder.
Expected: the workbook opens; Model!B15 shows a deterministic total of 9,750 $k and B17 shows 750 $k headroom.
2 | Make it probabilistic in one shot.
PROMPT → Build a Monte Carlo model from this brief: replace each base cost in Model!B6:B13 with the matching distribution from column D, using the WBS line names as input names; wrap Total cost B15 as output "TotalCost"; then run 5,000 iterations.
Expected: B6:B13 become VoseInput-wrapped PERT formulas, B15 becomes output "TotalCost", and a 5,000-iteration simulation completes.
3 | Forward view first: how bad is it, looking forwards?
PROMPT → What is the chance the total exceeds the 10,500 budget, and the P90 total?
Expected: a breach probability (roughly 10-25%) and a P90 total somewhat above the 10,500 budget.
4 | Now the reverse stress test: condition on the bad outcomes and ask what caused them.
PROMPT → Run a reverse stress test: when TotalCost breaches 10,500, which inputs are driving it, and what does the typical breach scenario look like?
Expected: a breach-driver ranking — each input’s shift in its own SDs inside the breach set — plus a named mean-input-vector stress scenario (reverse_stress_test).
5 | Vary the question: define the breach relatively instead of by the fixed budget.
PROMPT → Same again but define a breach as the worst 5% of outcomes instead of the fixed budget.
Expected: the same driver analysis run with threshold_percentile=0.95; rankings usually similar, thresholds differ.
WHAT TO LOOK FOR
• This is the Solvency-II-style question "what kills us?" — answered from the recorded joint samples, not from summary statistics.
• The driver ranking is conditional: it measures how far each input sits from its own mean (in its own SDs) inside the breach set only.
• The typical-breach scenario is a concrete, defensible input vector you can hand to engineers: "this is what a blown budget looks like".
• It needs the engine’s per-iteration input+output matrix — a tornado chart alone cannot answer it.
COLOUR LEGEND
Light blue + blue text: an input you can change
Pale yellow: where Claude will write Vose formulas / results land
Green bold: the key decision metric
Grey italic: a prompt to type to Claude

## Model
Data-centre build — cost model ($k)
8 WBS lines, hard budget 10,500 $k. Column D holds the distribution each base cost should become.
WORK BREAKDOWN
WBS line | Base cost ($k) | Suggested distribution (text)
Land & site | 950 | VosePERT(880,950,1150)
Shell & core | 2400 | VosePERT(2200,2400,3100)
Power train | 1900 | VosePERT(1750,1900,2500)
Cooling | 1450 | VosePERT(1300,1450,1950)
Racks & cabling | 1200 | VosePERT(1100,1200,1500)
Network | 600 | VosePERT(550,600,780)
Fit-out | 800 | VosePERT(720,800,1000)
Professional fees | 450 | VosePERT(420,450,560)
Total cost ($k) | 9750 | Claude will wrap B15 as output "TotalCost" and replace B6:B13 with the column-D distributions.
Budget ($k) | 10500
Headroom ($k) | 750 | Source: synthetic demo data, seed=n/a (hand-specified base costs), generated 2026-07-05